## User Stories
Story ID | Module | Screen | User Story | Acceptance Criteria | Category (AI / Non-AI) | Priority | Depends On Screen | Frontend Estimates (Days) | Backend Estimates (Days)
US-AUTH-01 | Authentication | Login (/) | As a user, I want to sign in with email and OTP so that I can access my relevant app experience. | Email entry is required; OTP step appears after Continue; Verify action signs user in and routes to persona home. | Non-AI | High | None (Entry Point) | 1
US-AUTH-02 | Authentication | Login (/) | As an investor user, I want to land on Dashboard after login so that I can quickly view portfolio health. | Investor persona is routed to /dashboard immediately after successful sign-in. | Non-AI | High | Login (/) | 0.5
US-AUTH-03 | Authentication | Login (/) | As a prospect user, I want to land on Explore after login so that I can discover investment opportunities. | Prospect persona is routed to /explore immediately after successful sign-in. | Non-AI | High | Login (/) | 0.5
US-AUTH-04 | Authorization | Investor-only Routes | As a prospect, I should be blocked from investor-only screens so that I only see allowed functionality. | Access to /dashboard, /portfolio, /property/:id, /documents redirects prospect to /explore. | Non-AI | High | Login (/) | 0.5
US-DASH-01 | Overview | Dashboard (/dashboard) | As an investor, I want to see key portfolio KPIs in one view so that I understand my current position quickly. | Shows Total Portfolio Value (or Property Value for single holding), capital growth £/% for selected range, Invested, Equity, Loans, Gross Yield, and Net Cash Flow. | Non-AI | High | Login (/) | 1.5
US-DASH-02 | Overview | Dashboard (/dashboard) | As an investor, I want portfolio highlights so that I can quickly identify top-performing assets. | Highlights section shows Best Performer, Highest Gross Yield (when available), Avg Gross Yield, and optional region blurb; each highlight deep-links to the related property where applicable. | Non-AI | High | Dashboard (/dashboard) | 1
US-DASH-03 | Overview | Dashboard (/dashboard) | As an investor, I want AI-generated portfolio insights so that I can understand risks, opportunities, and recommended next actions. | Insights cards are generated by an AI agent from portfolio context (e.g. concentration, regional yield gaps, yield vs target, growth vs cash flow, pipeline); each card shows tone/metric and can CTA to Explore when relevant. | AI | High | Dashboard (/dashboard) | 1
US-DASH-04 | Overview | Dashboard (/dashboard) | As an investor, I want to navigate from dashboard to deeper pages so that I can continue analysis. | Dashboard provides paths to Portfolio, Property Detail, Explore, Calculator, and Documents; time-range control (1M/3M/1Y/All) updates chart and growth metrics. | Non-AI | High | Dashboard (/dashboard) | 0.5
US-PF-01 | Portfolio | Portfolio (/portfolio) | As an investor, I want to see all my holdings with summary metrics so that I can compare properties quickly. | Header shows holdings count and total portfolio value; each card shows image, reference, status, name, location, Value, Rent, Gross Yield, and capital growth % when available; mortgaged cards show Monthly, Outstanding, progress, and Next due. | Non-AI | High | Dashboard (/dashboard) | 1
US-PF-02 | Portfolio | Portfolio (/portfolio) | As an investor, I want to open a property from portfolio so that I can view complete property-level details. | Tapping a holding card opens /property/:id for the selected property. | Non-AI | High | Portfolio (/portfolio) | 0.5
US-PF-03 | Portfolio | Portfolio (/portfolio) | As an investor, I want an advisor CTA on portfolio so that I can request help while reviewing holdings. | Portfolio footer exposes Speak with advisor / contact flow. | Non-AI | Medium | Portfolio (/portfolio) | 0.5
US-PD-01 | Property Detail | Property Detail (/property/:id) | As an investor, I want a property hero and overview so that I can confirm the asset basics and valuation position. | Hero shows image, reference, status, name, location, beds/baths/sq ft. Overview shows current valuation, capital growth since purchase, Purchase Price, Current Value, Equity, and Outstanding Loan with LTV. | Non-AI | High | Portfolio (/portfolio) | 1
US-PD-02 | Property Detail | Property Detail (/property/:id) | As an investor, I want a Mortgage Plan section on owned leveraged holdings so that I can track repayments and schedule. | Mortgage tab appears only when a plan exists; shows lender, type, rate, monthly, outstanding, term, original loan, progress, next payment, and schedule filterable by All/Paid/Due/Upcoming. | Non-AI | High | Property Detail (/property/:id) | 1.5
US-PD-03 | Property Detail | Property Detail (/property/:id) | As an investor, I want Income & Costs details so that I can see rent versus operating expenses and net cash flow. | Tenanted holdings show monthly rent vs expected, Service Charge, Management Fee, Mortgage, Total Costs, Net Monthly and Annual. In Build holdings show expected-rent empty state. | Non-AI | High | Property Detail (/property/:id) | 1
US-PD-04 | Property Detail | Property Detail (/property/:id) | As an investor, I want Performance metrics so that I can compare growth, yield, and occupancy for the property. | Performance section shows Capital Growth %, Gross Yield (or em dash when not applicable), and Occupancy %. | Non-AI | High | Property Detail (/property/:id) | 0.5
US-PD-05 | Property Detail | Property Detail (/property/:id) | As an investor, I want Value Over Time and long-term Projection so that I can evaluate historical and forward-looking returns. | Value chart supports 1M/3M/1Y/All. Projection supports 5Y/10Y/15Y with capital growth, cumulative income, total return, year-by-year breakdown, and assumptions disclaimer. | Non-AI | High | Property Detail (/property/:id) | 1
US-PD-06 | Property Detail | Property Detail (/property/:id) | As an investor, I want Tenancy details when a tenant exists so that I can track occupancy end dates. | Tenancy section appears only when tenant data exists and shows tenant name, end date, and occupancy. | Non-AI | Medium | Property Detail (/property/:id) | 0.5
US-DOC-01 | Documents | Documents (/documents) | As an investor, I want to search and filter my document library so that I can quickly find required files. | Category filters (All, Contracts, Rental, Tax, Mortgage, Legal, Others) and search by name narrow results; header shows file count and new count. | Non-AI | High | Dashboard (/dashboard) | 1
US-DOC-02 | Documents | Documents (/documents) | As an investor, I want to upload and access documents so that portfolio paperwork stays centralized. | Upload adds document to library; open/download is available per item; filtered empty state offers upload CTA. | Non-AI | Medium | Documents (/documents) | 1
US-EXP-01 | Explore | Explore (/explore) | As a user, I want to browse curated opportunities so that I can discover suitable investments. | Header shows curated and available counts; cards show status, reference, city, name, unit types, completion, From price, Gross Yield Est., and 5-Yr Forecast. | Non-AI | High | Login (/) OR Bottom Nav | 1
US-EXP-02 | Explore | Explore (/explore) | As a user, I want to filter opportunities by City, Budget, and Gross Yield so that results match my interest. | Filters update result count; chips and Reset restore defaults; empty filter state is shown when no matches. | Non-AI | High | Explore (/explore) | 0.5
US-EXP-03 | Explore | Explore (/explore) | As a user, I want to open an opportunity for full details so that I can evaluate before contacting advisor. | Selecting an opportunity opens /explore/:id with contextual data. | Non-AI | High | Explore (/explore) | 0.5
US-OPP-01 | Opportunity Detail | Opportunity Detail (/explore/:id) | As a user, I want opportunity hero and at-a-glance metrics so that I can assess price, yield, and availability quickly. | Shows image, status, reference, name, developer, location, tagline, Starting price, 5Y forecast, Gross Yield Est., Completion/tenure, and Availability (units available/total). | Non-AI | High | Explore (/explore) | 1
US-OPP-02 | Opportunity Detail | Opportunity Detail (/explore/:id) | As a user, I want Why This Opportunity and Key Facts so that I understand the investment narrative and essentials. | Highlights bullets and Key Facts (developer, location/postcode, completion, tenure/lease years) are displayed. | Non-AI | High | Opportunity Detail (/explore/:id) | 0.5
US-OPP-03 | Opportunity Detail | Opportunity Detail (/explore/:id) | As a user, I want an illustrative Mortgage Plan on the opportunity so that I can estimate deposit, loan, and monthly cost. | Available opportunities show illustrative deposit/loan/monthly/rate with personalisation note; sold-out/closed opportunities show summary state instead of a fake live schedule. | Non-AI | High | Opportunity Detail (/explore/:id) | 0.5
US-OPP-04 | Opportunity Detail | Opportunity Detail (/explore/:id) | As a user, I want opportunity Projection outputs so that I can review capital growth, income, and total return horizons. | Projection section supports 5Y/10Y/15Y with capital growth, cumulative income, total return, chart/year breakdown, and assumptions. | Non-AI | High | Opportunity Detail (/explore/:id) | 1
US-OPP-05 | Opportunity Detail | Opportunity Detail (/explore/:id) | As a user, I want a clear Contact Sales action so that I can request advisor follow-up from this opportunity context. | Bottom nav is hidden; sticky Contact Sales opens advisor sheet with selected opportunity context; optional #contact deep-link opens sheet on load. | Non-AI | High | Opportunity Detail (/explore/:id) | 0.5
US-CAL-01 | Calculator | Calculator — Deposit Step (/calculator) | As a user, I want to enter deposit, risk appetite, and investment horizon so that the calculator can start affordability modelling. | Inputs: Deposit Amount (£), Risk Appetite (Low/Med/High → suggested LTV 55/65/75), Investment Horizon (5/10/15 years). Continue is disabled below minimum deposit (£1,000). Progress shows 5-step wizard. | Non-AI | High | Bottom Nav (Dashboard/Explore) | 1
US-CAL-02 | Calculator | Calculator — Affordability Step (/calculator) | As a user, I want to configure Mortgage vs Cash and LTV so that I can see my estimated property budget and monthly mortgage. | Inputs: Investment Type (Mortgage/Cash), LTV slider (50–80% when Mortgage), Mortgage Type (Interest-only/Repayment). Outputs: Estimated property budget, Deposit/Loan/LTV breakdown, and monthly mortgage estimate using nationality-aware illustrative rate. | Non-AI | High | Calculator — Deposit Step (/calculator) | 1
US-CAL-03 | Calculator | Calculator — Options Step (/calculator) | As a user, I want matched opportunities against my budget so that I can shortlist realistic developments. | Shows matched cards with Matches budget / Stretch badges, From price, Gross Yield, 5Y Growth; city refine chips; empty-match guidance when none fit. Selecting a card advances to Returns. | Non-AI | High | Calculator — Affordability Step (/calculator) | 1
US-CAL-04 | Calculator | Calculator — Options Step (/calculator) | As a user, I want to refine development, unit type, purchase price, and nationality so that returns use my chosen deal setup. | Refine inputs: Development, Unit Type, Purchase Price (editable), City (readonly). Investor Setup: Nationality (UK Resident / Non-UK → rates 5.25%/6.25%), Mortgage Type when mortgaged. Derived costs use yield-based rent, service charge ~0.5% value, management ~10% rent. | Non-AI | High | Calculator — Options Step (/calculator) | 1
US-CAL-05 | Calculator | Calculator — Returns Step (/calculator) | As a user, I want detailed return metrics and cash-required budget so that I understand income and upfront cost. | Outputs: Total Return (£ and % over horizon), Monthly/Annual Rental Income, Net Monthly Income, Gross Yield Y1, Initial Cash Required (deposit or full price + SDLT UK 3%/Non-UK 5% + legal £2,500), Projected Future Value, plus Quick Look narrative and CTA to full projection. | Non-AI | High | Calculator — Options Step (/calculator) | 1
US-CAL-06 | Calculator | Calculator — Projection Step (/calculator) | As a user, I want long-term projection charts and assumption details so that I can evaluate capital growth and cumulative income. | Inputs: Holding period tabs 5/10/15. Outputs: Total Return headline, Capital Growth, Cumulative net Rental Income, property-value and cumulative-income charts, year outlook. Assumptions accordion shows capital growth 4.5%/yr, rental growth 3%, mortgage rate (or N/A), management 10% of rent, service charge 0.5% of value, cost inflation 2.5%. Speak to Advisor CTA available. | Non-AI | High | Calculator — Returns Step (/calculator) | 1
US-CAL-07 | Calculator | Run Numbers (/calculator/:source/:id) | As a user, I want a seeded Run Numbers calculator from a property or opportunity so that I can model one asset with editable assumptions. | Seeded from property or explore source. Editable inputs: Property Price, Monthly Rent, Capital Growth %, Rental Growth %, Holding Period (5/10/15/20), Management Fee, Service Charge, Mortgage (annual), Reset. Outputs: Total Return £/%, Net Annual Income, Gross Yield Y1, Capital Growth £/%, Projected Future Value, Cumulative Income, Avg Net Income/Yr, and CTA back to source projection. | Non-AI | Medium | Property Detail (/property/:id) OR Opportunity Detail (/explore/:id) | 0.5
US-ADV-01 | Advisor Contact | Global Contact Flow | As a user, I want to contact an advisor from key screens so that I can get assisted guidance anytime. | Contact entry points exist from Dashboard, Portfolio, Opportunity Detail, Calculator, and Profile. | Non-AI | High | Dashboard/Portfolio/Opportunity Detail/Calculator/Profile | 0.5
US-ADV-02 | Advisor Contact | Global Contact Flow | As a user, I want channel choices (call/callback/email) so that I can choose my preferred communication method. | Contact sheet shows Schedule a call, Request callback, and Email; each path shows success confirmation; opportunity context included when opened from Explore detail. | Non-AI | High | Any screen with Contact CTA | 0.5
US-SHELL-01 | Navigation | App Shell + Bottom Nav | As a user, I want persona-specific navigation so that I only see relevant sections. | Investor sees Overview, Portfolio, Explore, Calc, Docs; Prospect sees Explore, Calc. | Non-AI | High | Login (/) | 0.5
US-EMPTY-01 | Empty States | Preview/Empty States | As product/design QA, I want empty and partial states available so that zero-data scenarios are validated. | Empty/partial states are available for Overview, Portfolio, Documents, Explore, and Calculator and visually distinguish no-data conditions. | Non-AI | Medium | Preview Hub (/preview) | 0.5
US-GA-01 | Analytics | App-wide (Google Analytics) | As a product stakeholder, I want Google Analytics integrated across the investor app so that key user journeys and screen usage can be tracked. | Google Analytics is configured in the frontend; page views and key funnel events (login, explore, calculator steps, contact advisor) are tracked without blocking core app flows. | Non-AI | High | App Shell + authenticated screens | 0.5
US-GA-02 | Analytics | Google Analytics reporting | As a stakeholder, I want Google Analytics records to be fetched directly by Osama or Rizwan so that reporting access stays with the designated owners. | GA property/reporting access is owned by Osama or Rizwan; they fetch/export analytics records directly from Google Analytics (no in-app analytics admin required for V1). | Non-AI | Medium | US-GA-01 (Google Analytics integration) | 0.5