## Slide 1
Joseph Mews: 7-Week Delivery Plan
Initial App Store Submission: 21 August | TestFlight Build: 26 August | Delivery Target: 18 September
Required from Joseph Mews: named project sponsor, approved knowledge base content, CRM requirements and access, projection calculations, and Apple/Android developer account information.
Phase / Workstream
Wk 1
3 Aug
Wk 2
10 Aug
Wk 3
17 Aug
Wk 4
24 Aug
Wk 5
31 Aug
Wk 6
7 Sep
Wk 7
14 Sep
Core Infrastructure & Access
Application environments, authentication, user access, core data model and platform foundations
Portfolio, Properties & Documents
Investor portfolio, property details, payment schedules and property-specific document management
Projections & Financial Tools
Investment projections, calculator journeys, assumptions, mortgage information and financial outputs
CRM, Engagement & WhatsApp
CRM synchronisation, investor activity signals, administration workflows and WhatsApp experience
Testing & Launch Readiness
Integration testing, stakeholder testing, issue resolution, store updates and production readiness
TODAY
Initial App Store
submission, 21 Aug
TestFlight build
available, 26 Aug
Timeline indicative and dependent on timely content approvals, projection calculations, CRM access, developer account setup and stakeholder feedback.