JOSEPH MEWS — CORE APP + ADMIN PANEL + QIKO AI · DEPLOYMENT PLAN & RESOURCES

7 WEEKS · Start Mon 3 Aug 2026 → QA / Go-live w/c 14 Sep 2026 · PUBLIC HOLIDAYS: Fri 14 Aug · Tue 25 Aug · Core ~40 stories + Admin ~50 stories + Qiko AI 13 packages (21d) · Resources: Backend · App Developer · Frontend (Admin only) · AI Architect

PUBLIC HOLIDAYS (non-working): Friday 14 August 2026 · Tuesday 25 August 2026. Aug Wk 2 and Aug Wk 4 are 4-day weeks (33 working days/person across 7 weeks). Week 7 (14–18 Sep) is QA / UAT then go-live.

1. SCOPE SUMMARY

| Surface | Stories / Packages | Primary owner | Effort |
| --- | --- | --- | --- |
| Core App | 40 stories | App Developer + Backend | ~59 person-days |
| Admin Panel | 50 stories | Frontend Developer + Backend | ~58.5 person-days |
| Qiko AI Worker | 13 packages (QAI-01…13) | AI Architect | 21 active days |

2. RESOURCES

| Role | Focus |
| --- | --- |
| Backend Developer | Auth, data model, APIs, Admin↔Core wiring, JM↔Qiko turn integration, CRM sync, deploy |
| App Developer | Core / investor-facing app only — shell, Dashboard, Portfolio, Property, Docs, Explore, Calculator, Contact |
| Frontend Developer | Admin panel only — Users/Roles, dashboard, CRM, Properties, Assumptions, Payments, Enquiries, CMS, Signals UI |
| AI Architect | Qiko AI only — QAI-01…QAI-13: headless API, conversation state, RAG, intent/handoff/booking, nurture, insights, hardening |

3. PHASE OVERVIEW (calendar weeks)

| Phase | Timing | Focus |
| --- | --- | --- |
| PHASE 1: Discovery & Foundations | Aug Wk 1 (3–7 Aug) | Kick-off, auth, RBAC, data model, shells, JM↔Qiko contract freeze, QAI-01 |
| PHASE 2: Core App MVP | Aug Wk 2–4 (10–28 Aug) | Login → Dashboard → Portfolio → Property → Docs → Explore → Calculator → Contact |
| PHASE 3: Admin Panel Build | Aug Wk 2 – Sep Wk 1 | CRM, Properties, Assumptions SSOT, Payments, Enquiries, CMS, Audit |
| PHASE 4: Qiko AI + Intel & E2E | Aug Wk 2 – Sep Wk 2 | QAI-02…13, JM↔Qiko wiring, signals, CRM sync, E2E |
| PHASE 5: QA, Go-Live & Handover | Sep Wk 3 (14–18 Sep) | Full QA/UAT week, production deploy, training, hypercare |

PHASE 1: DISCOVERY & FOUNDATIONS

| Task | Days | Owner | Weeks |
| --- | --- | --- | --- |
| Kick-off & scope lock — Core + Admin + JM↔Qiko AI contract freeze | 2 | Backend / AI Architect | Aug W1 |
| Auth foundation — email OTP (Core) + staff login / RBAC (Admin) | 4 | Backend Developer | Aug W1 |
| Core data model + shared calculation service | 5 | Backend Developer | Aug W1 |
| Core App shell + persona nav | 2 | App Developer | Aug W1 |
| Admin shell + protected routes | 2 | Frontend Developer | Aug W1 |
| QAI-01 Production headless API foundation | 4 | AI Architect | Aug W1–W2 |

PHASE 2: CORE APP MVP (App Developer + Backend)

| Task | Days | Owner | Weeks |
| --- | --- | --- | --- |
| Login UI + OTP / session / invite-only routing | 4 | App Dev / Backend | Aug W2 |
| Dashboard — KPIs, highlights, charts (ex-AI cards) | 4 | App Dev / Backend | Aug W2 |
| Portfolio holdings list + property navigation | 2 | App Dev / Backend | Aug W2 |
| Property Detail — overview, mortgage, income, projection, tenancy | 8 | App Dev / Backend | Aug W2–W3 |
| Documents — search, filters, upload, download | 3 | App Dev / Backend | Aug W3 |
| Explore + Opportunity Detail + Contact Sales | 6 | App Dev / Backend | Aug W3–W4 |
| Calculator wizard (5 steps) + Run Numbers | 7 | App Dev / Backend | Aug W3–W4 |
| Advisor contact + empty states + activity logging | 4 | App Dev / Backend | Aug W4 |
| Wire Core fixtures → live Admin APIs | 3 | App Dev / Backend | Aug W4 – Sep W1 |

PHASE 3: ADMIN PANEL BUILD (Frontend Developer + Backend)

| Task | Days | Owner | Weeks |
| --- | --- | --- | --- |
| Users & Roles — invite, activate/deactivate, role assignment | 2 | Frontend / Backend | Aug W2 |
| Admin dashboard — KPIs, Agent scope, deep links | 3 | Frontend / Backend | Aug W2–W3 |
| Developments + Properties inventory (CRUD, publish/unpublish) | 6 | Frontend / Backend | Aug W2–W3 |
| Calculations & Assumptions workspace (SSOT, scopes, versioning) | 8 | Frontend / Backend | Aug W3–W4 |
| Wire Core calculators / portfolio math → Admin assumptions | 3 | Backend Developer | Aug W4 |
| Investor CRM — list, create, invite, detail workspace | 8 | Frontend / Backend | Aug W3–W4 |
| Ownership assignment + payment plans + payment schedules | 6 | Frontend / Backend | Aug W4 – Sep W1 |
| Enquiries pipeline + document visibility + Content CMS | 5 | Frontend / Backend | Sep W1 |
| Audit log + global settings (banner, invite-only) | 2 | Frontend / Backend | Sep W1 |

PHASE 4: QIKO AI WORKER + INTELLIGENCE & INTEGRATIONS

| Task | Days | Owner | Weeks |
| --- | --- | --- | --- |
| QAI-02 Durable conversation state | 2 | AI Architect | Aug W2 |
| QAI-03 Knowledge lifecycle + tenant RAG | 2 | AI Architect | Aug W2–W3 |
| QAI-04/05/06 Registration, adaptive tone, qualification | 2 | AI Architect | Aug W3 |
| QAI-07 Grounding, refusal & AI evals | 2 | AI Architect | Aug W3–W4 |
| QAI-08/09 Intent, fast-track & human handoff packet | 3 | AI Architect | Aug W4 |
| QAI-10/11 Booking decisioning + nurture / messaging policy | 2.5 | AI Architect | Sep W1 |
| QAI-12 Portfolio insights & signal summaries (US-DASH-03) | 1.5 | AI Architect | Sep W1 |
| QAI-13 Production hardening & observability | 2 | AI Architect | Sep W2 |
| JM↔Qiko WhatsApp AI turn integration | 3 | Backend Developer | Aug W4 – Sep W1 |
| Intent signals engine + configurable rules (Admin) | 3 | Frontend / Backend | Sep W1 |
| App UI wire — AI insight cards + Admin signal summaries | 2 | App Dev / Frontend | Sep W1–W2 |
| Assumption impact preview + in-app / email notifications | 3 | Frontend / Backend | Sep W1 |
| Two-way CRM sync — investor data + assignments | 3 | Backend Developer | Sep W1–W2 |
| End-to-end integration tests — Core ↔ Admin ↔ Qiko AI | 3 | Backend / App / AI | Sep W2 |

PHASE 5: QA, GO-LIVE & HANDOVER (Week 7)

| Task | Days | Owner | Weeks |
| --- | --- | --- | --- |
| QA / UAT with Joseph Mews — Core, Admin, Qiko AI + bug fixes | 4 | All (BE / App / FE / AI) | Sep W3 |
| Production deployment (Core + Admin + Qiko worker) | 1.5 | Backend / AI Architect | Sep W3 |
| Training, docs & hypercare / activity reporting handoff | 1.5 | Backend / Frontend | Sep W3 |

4. QIKO AI PACKAGE ROLLUP (21 DAYS)

| ID | Task | Days | Plan week(s) | Story refs |
| --- | --- | --- | --- | --- |
| QAI-01 | Headless API foundation | 4 | Aug W1–W2 | WA Admin #2 |
| QAI-02 | Durable conversation state | 2 | Aug W2 | WA Cust R18 · WA Admin #14 |
| QAI-03 | Knowledge lifecycle + tenant RAG | 2 | Aug W2–W3 | WA Admin #11/#10 · WA Cust R10 |
| QAI-04 | Registration & permission flow | 0.5 | Aug W3 | WA Cust R3 · US-WA-01 |
| QAI-05 | Experience-adaptive tone | 0.5 | Aug W3 | WA Cust R4 · US-WA-02 |
| QAI-06 | Qualification extraction | 1 | Aug W3 | WA Cust R5/R13 · WA Admin #5 |
| QAI-07 | Grounding, refusal & AI evals | 2 | Aug W3–W4 | WA Cust R10 · Knowledge Base |
| QAI-08 | Intent & fast-track decisioning | 2 | Aug W4 | WA Cust R6 · Admin #24/#25 |
| QAI-09 | Human handoff decision & packet | 1 | Aug W4 | WA Cust R9/R19 · WA Admin #9 |
| QAI-10 | Booking action decisioning | 1 | Sep W1 | WA Cust R14 · US-WA-06 |
| QAI-11 | Nurture & messaging policy | 1.5 | Sep W1 | WA Cust R8/R12/R15 · WA Admin #8 |
| QAI-12 | Portfolio insights & signal summaries | 1.5 | Sep W1 | US-DASH-03 · Admin #50 |
| QAI-13 | Production hardening & observability | 2 | Sep W2 | Cross-cutting production gate |
| TOTAL |  | 21 | Complete by Sep W2; Wk 7 = QA |  |

Architecture boundary: JM owns auth, business data, UX, and WhatsApp transport. Every WhatsApp AI turn calls Qiko headless API. Qiko owns conversation logic, RAG, and AI state; JM executes returned actions. Excluded from AI 21d: WA/Interakt transport, CRM/Zapier writes, booking-provider APIs, Client/Admin app UI, Meta approval wait time.

5. CLIENT INPUTS NEEDED

1. Start confirmed: Week 1 = Mon 3 Aug 2026; QA / go-live week = w/c 14 Sep 2026

2. Acknowledge public holidays Fri 14 Aug and Tue 25 Aug

3. Freeze JM↔Qiko headless API contract, service auth, and WhatsApp AI turn schema (P0)

4. Supply approved knowledge-base content + confirm who accepts AI eval results

5. Confirm sandbox endpoints / test IDs for Qiko integration

6. Decision: CRM sync Day-1 required, or Admin as temporary system of record?

7. Decision: Assumptions versioning + preview Day-1, or edit + history first?

8. OTP / email provider credentials and branding templates

9. Document storage preference and retention policy

10. Sample investor, property, opportunity + WhatsApp lead seed data for UAT

11. Named UAT testers available in Week 7 (14–18 Sep)

12. CRM connector credentials + conflict rules (if Day-1 sync required)

13. Staff role matrix (Super Admin / Admin / Agent) for invite seed

14. Approve novice/experienced tone profiles, mandatory qualification fields, handoff SLA, booking conversion definition

15. Joseph Mews effort ~3–5 days across the build (reviews, UAT, content, knowledge approval)