## DEPLOYMENT
JOSEPH MEWS — CORE APP + ADMIN PANEL + QIKO AI · DEPLOYMENT PLAN & RESOURCES
DEPLOYMENT TIMELINE (7 WEEKS) · Start Mon 3 Aug 2026 → QA / Go-live w/c 14 Sep 2026 · PUBLIC HOLIDAYS: Fri 14 Aug · Tue 25 Aug · Core ~40 stories + Admin ~50 stories + Qiko AI 13 packages (21d) · BE + App + Admin FE + AI Architect in parallel
Task | Days | Owner | Aug Wk 1 3–7 Aug | Aug Wk 2 10–14 Aug 14 PH | Aug Wk 3 17–21 Aug | Aug Wk 4 24–28 Aug 25 PH | Sep Wk 1 31 Aug–4 Sep | Sep Wk 2 7–11 Sep | Sep Wk 3 14–18 Sep QA
PHASE 1: DISCOVERY & FOUNDATIONS
Kick-off & scope lock — Core + Admin + JM↔Qiko AI contract freeze | 2 | Backend / AI Architect
Auth foundation — email OTP (Core) + staff login / RBAC (Admin) | 4 | Backend Developer
Core data model + shared calculation service | 5 | Backend Developer
Core App shell + persona nav (Investor / Prospect) | 2 | App Developer
Admin shell + protected routes (Admin FE only) | 2 | Frontend Developer
QAI-01 Production headless API foundation (auth, ops, idempotency, tracing) | 4 | AI Architect
PHASE 2: CORE APP MVP (App Developer + Backend)
Login UI + OTP / session / invite-only routing | 4 | App Dev / Backend
Dashboard — KPIs, highlights, charts, deep links (ex-AI cards) | 4 | App Dev / Backend
Portfolio holdings list + property navigation | 2 | App Dev / Backend
Property Detail — overview, mortgage, income, projection, tenancy | 8 | App Dev / Backend
Documents — search, filters, upload, download | 3 | App Dev / Backend
Explore + Opportunity Detail + Contact Sales | 6 | App Dev / Backend
Calculator wizard (5 steps) + Run Numbers | 7 | App Dev / Backend
Advisor contact + empty states + activity logging | 4 | App Dev / Backend
Wire Core fixtures → live Admin APIs | 3 | App Dev / Backend
PHASE 3: ADMIN PANEL BUILD (Frontend Developer + Backend)
Users & Roles — invite, activate/deactivate, role assignment | 2 | Frontend / Backend
Admin dashboard — KPIs, Agent scope, deep links | 3 | Frontend / Backend
Developments + Properties inventory (CRUD, publish/unpublish) | 6 | Frontend / Backend
Calculations & Assumptions workspace (SSOT, scopes, versioning) | 8 | Frontend / Backend
Wire Core calculators / portfolio math → Admin assumptions | 3 | Backend Developer
Investor CRM — list, create, invite, detail workspace | 8 | Frontend / Backend
Ownership assignment + payment plans + payment schedules | 6 | Frontend / Backend
Enquiries pipeline + document visibility + Content CMS | 5 | Frontend / Backend
Audit log + global settings (banner, invite-only) | 2 | Frontend / Backend
PHASE 4: QIKO AI WORKER + INTELLIGENCE & INTEGRATIONS
QAI-02 Durable conversation state (tenant history, checkpoints) | 2 | AI Architect
QAI-03 Knowledge lifecycle + tenant RAG (ingestion, citations) | 2 | AI Architect
QAI-04/05/06 Registration, adaptive tone, qualification extraction | 2 | AI Architect
QAI-07 Grounding, refusal & AI evals (English-only, abstention) | 2 | AI Architect
QAI-08/09 Intent, fast-track & human handoff packet | 3 | AI Architect
QAI-10/11 Booking decisioning + nurture / messaging policy | 2.5 | AI Architect
QAI-12 Portfolio insights & signal summaries (US-DASH-03 / Admin #50) | 1.5 | AI Architect
QAI-13 Production hardening & observability (security, recovery) | 2 | AI Architect
JM↔Qiko WhatsApp AI turn integration (schema, auth, actions) | 3 | Backend Developer
Intent signals engine + configurable rules (Admin) | 3 | Frontend / Backend
App UI wire — AI insight cards + Admin signal summaries | 2 | App Dev / Frontend
Assumption impact preview + in-app / email notifications | 3 | Frontend / Backend
Two-way CRM sync — investor data + assignments | 3 | Backend Developer
End-to-end integration tests — Core ↔ Admin ↔ Qiko AI | 3 | Backend / App / AI
PHASE 5: QA, GO-LIVE & HANDOVER (Week 7)
QA / UAT with Joseph Mews — Core, Admin, Qiko AI flows + bug fixes | 4 | All (BE / App / FE / AI)
Production deployment (Core App + Admin Panel + Qiko worker) | 1.5 | Backend / AI Architect
Training, docs & hypercare / activity reporting handoff | 1.5 | Backend / Frontend
PUBLIC HOLIDAYS (non-working): Friday 14 August 2026 · Tuesday 25 August 2026 — Aug Wk 2 and Aug Wk 4 are 4-day weeks. Plan capacity assumes 33 working days / person across 7 weeks (not 35).
LEGEND:
Discovery & Foundations
Core App MVP (App Developer)
Admin Panel Build (Frontend Developer)
Qiko AI Worker (AI Architect)
Intelligence, Integrations & E2E
QA / Go-Live & Handover (Week 7)
RESOURCES
Backend Developer | Auth, data model, APIs, Admin↔Core wiring, JM↔Qiko turn integration, CRM sync, deploy
App Developer | Core / investor-facing app only — shell, Dashboard, Portfolio, Property, Docs, Explore, Calculator, Contact
Frontend Developer | Admin panel only — Users/Roles, Admin dashboard, CRM, Properties, Assumptions, Payments, Enquiries, CMS, Signals UI
AI Architect | Qiko AI only — QAI-01…QAI-13 (21 active days): headless API, conversation, RAG, intent/handoff/booking, nurture, insights, hardening
EFFORT DISTRIBUTION (7-WEEK COMPRESSED — AI IN PARALLEL)
Phase | Days | Weeks | Distribution notes
1. Foundations | 19.0 | Wk 1–2 | Auth, model, shells + QAI-01 API foundation; contract freeze Day 1
2. Core App MVP | 41.0 | Wk 2–4 | App Developer + Backend; overlaps Admin; 14 Aug PH in Wk 2
3. Admin Panel | 43.0 | Wk 2–5 | Frontend Developer (Admin only) + Backend; 25 Aug PH in Wk 4
4. Qiko AI + Intel | 32.0 | Wk 2–6 | AI Architect QAI-02…13 (17d) + JM wiring, signals, CRM, E2E
5. QA / Go-Live | 7.0 | Wk 7 | Full QA/UAT week (14–18 Sep) then deploy, train, hypercare
Team model: 1× Backend + 1× App Developer + 1× Frontend (Admin only) + 1× AI Architect. Qiko AI (21 active days) runs in parallel from Wk 1 and must not extend the 7-week calendar. Week 7 is reserved for QA/UAT then go-live. Assumptions / Properties must land by Wk 4–5 before Core goes live on real data. AI P0 blockers (API contract, auth, WA turn schema, approved knowledge, sandbox IDs) freeze in Wk 1 kick-off.
CLIENT INPUTS NEEDED
1. Start confirmed: Week 1 = Mon 3 Aug 2026; go-live / QA week = w/c 14 Sep 2026
2. Acknowledge public holidays Fri 14 Aug and Tue 25 Aug (4-day weeks in Aug Wk 2 and Aug Wk 4)
3. Named project sponsor available for weekly check-ins
4. Freeze JM↔Qiko headless API contract, service auth, and WhatsApp AI turn request/response schema (P0)
5. Supply approved knowledge-base content + confirm who accepts AI eval results
6. Confirm sandbox endpoints / test IDs for Qiko integration
7. Decision: CRM sync Day-1 required, or Admin as temporary system of record?
8. Decision: Assumptions versioning + preview Day-1, or edit + history first / preview later?
9. OTP / email provider credentials and branding templates
10. Document storage preference and retention policy
11. Sample investor, property, opportunity + WhatsApp lead seed data for UAT
12. Named UAT testers available in Week 7 (14–18 Sep)
13. CRM connector credentials + conflict rules (if Day-1 sync is required)
14. Staff role matrix (Super Admin / Admin / Agent) for invite seed
15. Approve novice/experienced tone profiles, mandatory qualification fields, handoff SLA, booking conversion definition
16. Joseph Mews effort estimate: approximately 3–5 days across the build (reviews, UAT, content, knowledge approval)

## STORY COVERAGE
STORY COVERAGE MAP — 7-week plan (Core + Admin + Qiko AI)
Work package (Gantt task) | Covers modules / stories | Surface | Phase
Auth foundation — OTP + staff login / RBAC | Authentication, Authorization, Platform & Access, Users & Roles (partial) | Both | 1
Core data model + shared calculation service | All Core metrics + Admin Assumptions engine foundation | Both | 1
QAI-01 Headless API foundation | WA Admin #2 · all headless AI operations | Qiko AI | 1
Dashboard / Portfolio / Property / Docs | US-DASH-01/02/04, US-PF-01..03, US-PD-01..06, US-DOC-01/02 | Core | 2
Explore + Opportunity + Contact Sales | Explore, Opportunity Detail, Advisor Contact | Core | 2
Calculator wizard + Run Numbers | Calculator (US-CAL-01..07) | Core | 2
Developments + Properties inventory | Developments, Properties, publish → Explore | Admin | 3
Calculations & Assumptions (SSOT) | Calculations & Assumptions (14 stories) | Admin | 3
Investor CRM workspace | Investor CRM, Onboarding, Investor Detail / Portfolio | Admin | 3
Ownership + payment plans + schedules | Property Payment Plans, Payment Schedules | Admin | 3
Enquiries + docs + CMS + audit | Enquiries, Documents, Content CMS, Activity & Audit, Settings | Admin | 3
QAI-02 Durable conversation state | WA Customer R18 · WA Admin #14 | Qiko AI | 4
QAI-03 Knowledge lifecycle + tenant RAG | WA Admin #11 · WA Customer R10 · WA Admin #10 | Qiko AI | 4
QAI-04/05/06 Registration, tone, qualification | WA Customer R3/R4/R5/R13 · WA Admin #3/#4/#5 · US-WA-01/02 | Qiko AI | 4
QAI-07 Grounding, refusal & AI evals | WA Customer R10 · WA Admin #10 · Knowledge Base | Qiko AI | 4
QAI-08/09 Intent, fast-track & handoff | WA Customer R6/R9/R19 · WA Admin #6/#9 · Admin #24/#25 | Qiko AI | 4
QAI-10/11 Booking + nurture policy | WA Customer R8/R12/R14/R15 · WA Admin #8 · US-WA-06 | Qiko AI | 4
QAI-12 Portfolio insights & signal summaries | Core US-DASH-03 · Admin #50 · Intent Signals | Qiko AI | 4
QAI-13 Production hardening | Cross-cutting production gate | Qiko AI | 4
JM↔Qiko turn integration | JM transport ownership; every WA AI turn calls Qiko headless API | Backend | 4
Intent signals + notifications + CRM sync | Intent Signals, Notifications, CRM Integration | Admin | 4
QA / UAT Week 7 | Full regression Core + Admin + Qiko AI acceptance | All | 5

## QIKO AI PACKAGES
QIKO AI — 13 WORK PACKAGES (21 ACTIVE DAYS) ALIGNED TO 7-WEEK PLAN
Source: Joseph_Mews_AI_Executive_Task_Estimate_EN.pdf (31 Jul 2026). Owner: AI Architect only. JM owns WhatsApp transport / CRM writes / app UX — excluded from 21-day AI estimate. Public holidays 14 Aug & 25 Aug reduce calendar capacity but AI parallel track still completes by Wk 6; Wk 7 = QA.
ID | Task | Days | Plan week(s) | Excel / story refs | Phase gate
QAI-01 | Production headless API foundation | 4 | Aug Wk 1–2 | WA Admin #2 · all headless AI ops | AI Core
QAI-02 | Durable conversation state | 2 | Aug Wk 2 | WA Customer R18 · WA Admin #14 | AI Core
QAI-03 | Knowledge lifecycle and tenant RAG | 2 | Aug Wk 2–3 | WA Admin #11 · WA Cust R10 · WA Admin #10 | AI Core
QAI-04 | Registration and permission flow | 0.5 | Aug Wk 3 | WA Cust R3 · WA Admin #3 · US-WA-01 | Vertical
QAI-05 | Experience-adaptive tone | 0.5 | Aug Wk 3 | WA Cust R4 · WA Admin #4 · US-WA-02 | Vertical
QAI-06 | Qualification extraction | 1 | Aug Wk 3 | WA Cust R5/R13 · WA Admin #5 | Vertical
QAI-07 | Grounding, refusal and AI evals | 2 | Aug Wk 3–4* | WA Cust R10 · WA Admin #10 · Knowledge Base | Prod gate
QAI-08 | Intent and fast-track decisioning | 2 | Aug Wk 4* | WA Cust R6 · WA Admin #6 · Admin #24/#25 | Vertical
QAI-09 | Human handoff decision and packet | 1 | Aug Wk 4* | WA Cust R9/R19 · WA Admin #9 | Vertical
QAI-10 | Booking action decisioning | 1 | Sep Wk 1 | WA Cust R14 · US-WA-06 | Vertical
QAI-11 | Nurture and messaging policy | 1.5 | Sep Wk 1 | WA Cust R8/R12/R15 · WA Admin #8 | Vertical
QAI-12 | Portfolio insights and signal summaries | 1.5 | Sep Wk 1 | Core US-DASH-03 · Admin #50 | Prod gate
QAI-13 | Production hardening and observability | 2 | Sep Wk 2 | Cross-cutting production gate | Prod gate
TOTAL |  | 21 | * Aug Wk 4 includes Tue 25 Aug PH (4-day week)
Architecture boundary: JM = separate web/mobile platform (auth, business data, UX, WhatsApp transport). Every WhatsApp AI turn calls Qiko headless API. Qiko owns conversation logic, RAG, AI state. JM executes returned actions. Excluded from AI 21d: WA/Interakt transport, CRM/Zapier writes, booking-provider APIs, Client/Admin app UI, external deploy ownership, content creation, Meta approval wait time.